## Happeas project
# | Name of the task | Performer | Start | Finish | Сontinuance h. | Сompletion | November | [24 empty] | December | [19 empty] | January | [19 empty] | February | [24 empty] | March | [19 empty] | April | [19 empty] | May
[10 empty] | Milestone 6 |  |  |  |  | Milestone 7 |  |  |  |  | Milestone 8 |  | Milestone 10 |  |  |  |  | Milestone 11 | [7 empty] | Milestone 6 |  |  |  |  | Milestone 7 |  |  |  |  | Milestone 8 |  | Milestone 10 |  |  |  |  | Milestone 11 | [22 empty] | Milestone 6 |  |  |  |  | Milestone 7 |  |  |  |  | Milestone 8 |  | Milestone 10 |  |  |  |  | Milestone 11 |  |  |  |  | Milestone 12 |  |  |  |  | Milestone 13 |  |  |  |  | Milestone 10 |  |  |  |  | Milestone 11 |  |  |  |  | Milestone 12 |  |  |  |  | Milestone 13 | [7 empty] | Milestone 16 |  |  |  |  | Milestone 17 |  |  |  |  | Milestone 18 |  |  |  |  | Milestone 19 |  |  |  |  | Milestone 20 |  |  |  |  | Milestone 21
[7 empty] | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | [15 empty] | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU
[7 empty] | Milestone 1 |  |  |  |  | Milestone 2 |  |  |  |  | Milestone 3 |  |  |  |  | Milestone 4 |  |  |  |  | Milestone 5 |  |  |  |  | Milestone 6 |  |  |  |  | Milestone 7 |  |  |  |  | Milestone 8 |  |  |  |  | Milestone 9 |  |  |  |  | Milestone 11 |  |  |  |  | Milestone 12 |  |  |  |  | Milestone 13 |  |  |  |  | Milestone 14 |  |  |  |  | WE: Milestone 15; Milestone 6 WE: Milestone 16; Milestone 7 WE: Milestone 17; Milestone 10 MO: Milestone 18; Milestone 11 MO: Milestone 19; Milestone 12 MO: Milestone 20; Milestone 13 MO: Milestone 21; Milestone 10 MO: Milestone 22; Milestone 11 MO: Milestone 23; Milestone 12 MO: Milestone 24; Milestone 13 MO: Milestone 24; Milestone 13 WE: Milestone 25; Milestone 16 WE: Milestone 26; Milestone 17 WE: Milestone 27; Milestone 18 WE: Milestone 28; Milestone 19 WE: Milestone 29; Milestone 20 WE: Milestone 30
[7 empty] | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR | MO | TU | WE | TH | FR
13 | Backend development preparation
13.1 | Setting up a Database locally in Mongo and Postgres | Dima | 2024-02-05 | 2024-02-05 | 2 |  | Milestone 16 MO: 2
13.2 | Creating a Microservice Template | Dima | 2024-02-05 | 2024-02-05 | 4 |  | Milestone 16 MO: 4
13.3 | Creating GitHub eco | Dima/Vlad | 2024-02-05 | 2024-02-05 | 1 | bar: Milestone 16 MO
13.4 | Cloud technologies (S3, Search Map) GET API KEY | Dima/Vlad | 2024-02-05 | 2024-02-05 | 1 | bar: Milestone 16 MO
14 | Microservice «Proxy»
14.1 | Architecture | Dima/Vlad/Bilal | 2024-02-06 | 2024-02-06 | 4 |  | Milestone 16 TU: 4
14.2 | Project implementation | Dima | 2024-02-06 | 2024-02-09 | 20 |  | Milestone 16 TU: 3; Milestone 16 WE: 6; Milestone 16 TH: 6; Milestone 16 FR: 5
15 | Microservice «Logging»
15.1 | Architecture | Dima/Vlad/Bilal | 2024-02-12 | 2024-02-12 | 2 |  | Milestone 17 MO: 2
15.2 | Project implementation | Dima | 2024-02-12 | 2024-02-12 | 6 |  | Milestone 17 MO: 6
16 | Microservice «Authorization and user management» | bar: Milestone 17 MO
16.1 | Architecture | Dima/Vlad/Bilal | 2024-02-13 | 2024-02-13 | 8 |  | Milestone 17 TU: 8
16.2 | Database design | Dima/Vlad/Bilal | 2024-02-14 | 2024-02-14 | 8 |  | Milestone 16 TH: 1; Milestone 16 FR: 2; Milestone 17 WE: 8
16.3 | Migrations (Create and Index keys) | Dima | 2024-02-15 | 2024-02-15 | 4 |  | Milestone 17 TH: 4
16.4 | Connect to Proxy (Design routes) | Dima | 2024-02-15 | 2024-02-15 | 2 |  | Milestone 17 TH: 2
16.5 | Auth (login / register / forgoten / reset) | Dima | 2024-02-16 | 2024-02-16 | 8 |  | Milestone 17 FR: 8
16.6 | Security | Dima | 2024-02-19 | 2024-02-19 | 2 |  | Milestone 18 MO: 2
16.7 | Role manager | Dima | 2024-02-19 | 2024-02-23 | 34 |  | Milestone 18 MO: 4; Milestone 18 TU: 8; Milestone 18 WE: 8; Milestone 18 TH: 8; Milestone 18 FR: 6
16.8 | Group manager | Dima | 2024-02-26 | 2024-02-26 | 8 |  | Milestone 19 MO: 8
16.9 | Handbook | Dima | 2024-02-27 | 2024-03-01 | 27 |  | Milestone 19 TU: 8; Milestone 19 WE: 8; Milestone 19 TH: 8; Milestone 19 FR: 3
17 | Microservice «IMPORT / Export»
17.1 | Architecture | Dima/Vlad | 2024-03-01 | 2024-03-01 | 2 |  | Milestone 19 FR: 2
17.2 | Project implementation | Dima | 2024-03-01 | 2024-03-05 | 18 |  | Milestone 19 FR: 2; Milestone 20 MO: 8; Milestone 20 TU: 8
18 | Microservice «FileManager»
18.1 | Architecture | Dima/Vlad | 2024-03-06 | 2024-03-06 | 3 |  | Milestone 20 WE: 3
18.2 | Database design | Dima/Vlad | 2024-03-06 | 2024-03-06 | 2 |  | Milestone 20 WE: 2
18.3 | Project implementation Local | Dima | 2024-03-06 | 2024-03-11 | 27 |  | Milestone 20 WE: 3; Milestone 20 TH: 8; Milestone 20 FR: 8; Milestone 21 MO: 8
18.4 | Project implementation AWS | Dima | 2024-03-12 | 2024-03-13 | 16 |  | Milestone 21 TU: 8; Milestone 21 WE: 8
19 | Microservice «Notification»
19.1 | Architecture | Dima/Vlad | 2024-03-14 | 2024-03-14 | 4 |  | Milestone 21 TH: 4
19.2 | Database design | Dima/Vlad | 2024-03-14 | 2024-03-14 | 4 |  | Milestone 21 TH: 4
19.3 | Actions CRUD | Dima | 2024-03-15 | 2024-03-15 | 4 |  | Milestone 21 FR: 4
19.4 | Communication CRUD And Templates | Dima | 2024-03-15 | 2024-03-19 | 20 |  | Milestone 21 FR: 4; Milestone 22 MO: 8; Milestone 22 TU: 8
19.5 | Worker send mail | Dima | 2024-03-20 | 2024-03-21 | 16 |  | Milestone 22 WE: 8; Milestone 22 TH: 8
19.6 | Worker send sms | Dima | 2024-03-22 | 2024-03-25 | 16 |  | Milestone 22 FR: 8; Milestone 23 MO: 8
19.7 | Newsletter and schedule | Dima | 2024-03-25 | 2024-03-27 | 24 |  | Milestone 23 TU: 8; Milestone 23 WE: 8; Milestone 23 TH: 8
20 | Microservice «Routes»
20.1 | Architecture | Dima/Vlad | 2024-03-28 | 2024-03-28 | 4 |  | Milestone 23 FR: 4
20.2 | Database design | Dima/Vlad | 2024-03-28 | 2024-03-28 | 2 |  | Milestone 23 FR: 2
20.3 | Project implementation CRUD | Dima | 2024-03-28 | 2024-04-03 | 24 |  | Milestone 23 FR: 2; Milestone 24 MO: 8; Milestone 24 TU: 8; Milestone 24 WE: 6
20.4 | Execution of the route | Dima | 2024-04-03 | 2024-04-08 | 24 |  | Milestone 24 WE: 2; Milestone 24 TH: 8; Milestone 24 FR: 8; Milestone 24 MO: 6
21 | Microservice «Questionnaire management»
21.1 | Architecture | Dima/Vlad | 2024-04-08 | 2024-04-09 | 4 |  | Milestone 24 MO: 2; Milestone 24 TU: 2
21.2 | Database design | Dima/Vlad | 2024-04-09 | 2024-04-09 | 4 |  | Milestone 24 TU: 4
21.3 | Creating Questionnaire | Dima | 2024-04-09 | 2024-04-15 | 32 |  | Milestone 24 TU: 2; Milestone 24 WE: 8; Milestone 24 TH: 8; Milestone 24 FR: 8; Milestone 25 MO: 6
21.4 | List and Filter | Dima | 2024-04-15 | 2024-04-18 | 24 |  | Milestone 25 MO: 2; Milestone 25 TU: 8; Milestone 25 WE: 8; Milestone 25 TH: 6
21.5 | Templates | Dima | 2024-04-19 | 2024-04-22 | 16 |  | Milestone 25 TH: 2; Milestone 25 FR: 8; Milestone 26 MO: 6